## Sheet1
GANTT CHART | [21 empty] | https://goo.gl/PlIwL0
| PROJECT TITLE | Cyberpunk Detective |  |  |  |  | NAME OF TEAM | [6 empty] | 5 JOKES
| DURATION | 120 hours |  |  |  |  | DATE | [6 empty] | 24/09/2026
[7 empty] | DAY ONE (24/09/2026) | [9 empty] | DAY TWO (25/09/2026) | [9 empty] | DAY THREE (26/09/2026) | [9 empty] | DAY Four (27/09/2026) | [9 empty] | DAY Five (28/09/2026) | [9 empty] | DAY Six (29/09/2026)
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Morning |  |  |  | Noon |  |  |  | Night |  | Morning |  |  |  | Noon |  |  |  | Night |  | Morning |  |  |  | Noon |  |  |  | Night |  | Morning |  |  |  | Noon |  |  |  | Night |  | Morning |  |  |  | Noon |  |  |  | Night |  | Morning |  |  |  | Noon
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6
1 | Requirement Analysis |  |  |  |  | 20 hours
1.1 | Study and analysis Software Requirements Specification (SRS) | All | 2026-09-24 | 2026-09-24 | 2 | 100% | bar: Morning 1 to Morning 4
1.2 | Define scope & Identify objectives | All | 2026-09-24 | 2026-09-29 | 3 | 100% | bar: Morning 1 to Noon 7
1.3 | Outline core functionalities (functional and non-functional requirements) | All | 2026-09-24 | 2026-09-29 | 3 | 100% | bar: Morning 1 to Night 10
1.4 | Discuss technical, operational, UI, and security constraints | All | 2026-09-24 | 2026-09-29 | 3 | 100% | bar: Morning 1 to Noon 7
1.5 | Analyze target audience, goals, and project scope | Trinh Tan Loc, Pham Thien Phuc | 2026-09-24 | 2026-09-29 | 3 | 100% | bar: Morning 1 to Night 10
1.6 | Define roles and responsibilities of each member team | Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 3 | 100% | bar: Morning 1 to Morning 4
1.7 | List tools and technologies | All | 2026-09-24 | 2026-09-29 | 3 | 100% | bar: Morning 1 to Night 10
2 | Game Design |  |  |  |  | 20 hours
2.1 | Design the application architecture diagram | Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 20 | 100% | bar: Noon 7 to Noon 6
2.2 | Design flowchart / gameplay loop | Pham Thien Phuc | 2026-09-24 | 2026-09-29 | 12 | 100% | bar: Night 9 to Morning 4
2.3 | Design level layouts (environments, obstacles, NPC) | Nguyen The Kiet | 2026-09-24 | 2026-09-29 | 40 | 100% | bar: Noon 5 to Morning 4
2.4 | Design characters, NPC, and item | Tran Quoc An, Trinh Tan Loc, Nguyen The Kiet | 2026-09-24 | 2026-09-29 | 18 | 100% | bar: Noon 8 to Noon 6
2.5 | Design UI (main menu, HUD) | Huynh Nhat Duy, Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 24 | 100% | bar: Night 10 to Morning 1
2.6 | Design mission | Pham Thien Phuc, Tran Quoc An | 2026-09-24 | 2026-09-29 | 20 | 100% | bar: Noon 5 to Morning 4
2.7 | Plan audio (background music, environmental effects) | Nguyen The Kiet, Tran Quoc An, Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 18 | 100% | bar: Noon 5 to Morning 3
3 | Development - Front-end (Unity + C#) |  |  |  |  | 25 hour
3.1 | Build game environments (maps, props, lighting, effects) | Nguyen The Kiet | 2026-09-24 | 2026-09-29 | 20 | 100% | bar: Night 9 to Noon 8
3.2 | Implement player movement and responsive controls | Tran Quoc An | 2026-09-24 | 2026-09-29 | 22 | 100% | bar: Night 9 to Night 9
3.3 | Programming enemy AI mechanics | Tran Quoc An | 2026-09-24 | 2026-09-29 | 16 | 100% | bar: Night 9 to Noon 6
3.4 | Programming the in-game mission system | Pham Thien Phuc | 2026-09-24 | 2026-09-29 | 24 | 100% | bar: Night 9 to Night 10
3.5 | Add environmental puzzle system | Pham Thien Phuc | 2026-09-24 | 2026-09-29 | 28 | 100% | bar: Night 9 to Morning 2
3.6 | Build inventory system | Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 20 | 100% | bar: Night 9 to Noon 8
3.7 | Integration of reward and collectible item systems | Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 22 | 100% | bar: Night 9 to Night 9
4 | Development - Back-end (logic & data) |  |  |  |  | 25 hours
4.1 | Implement save/load system (checkpoints, mission progress) | Nguyen The Kiet, Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 28 | 100% | bar: Night 9 to Morning 2
4.2 | Player Data & Quest State Handling | Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 12 | 100% | bar: Night 9 to Morning 4
4.3 | Optimize performance (asset bundles, pooling, baked lighting) | Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 22 | 100% | bar: Night 9 to Night 9
4.4 | AI system for enemies | Tran Quoc An | 2026-09-24 | 2026-09-29 | 14 | 100% | bar: Night 9 to Noon 5
5 | Testing & Debugging |  |  |  |  | 15 hours
5.1 | Write test cases for all features | Nguyen The Kiet | 2026-09-24 | 2026-09-29 | 4 | 100% | bar: Noon 6 to Noon 7
5.2 | Perform unit testing | Nguyen The Kiet, Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 6 | 100% | bar: Noon 7 to Night 9
5.3 | Perform integration testing (AI, puzzles, missions, inventory) | Huynh Nhat Duy, Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 2 | 100% | bar: Night 9
5.4 | Test performance (FPS, asset loading, memory leaks) | Trinh Tan Loc, Pham Thien Phuc | 2026-09-24 | 2026-09-29 | 4 | 100% | bar: Night 10 to Morning 1
6 | Documentation & Reporting |  |  |  |  | 10 hours
6.1 | Write installation and user manuals | Tran Quoc An | 2026-09-24 | 2026-09-29 | 20 | 100% | bar: Noon 8 to Noon 7
6.2 | Create design documentation (flowcharts, data flow, architecture) | Pham Thien Phuc | 2026-09-24 | 2026-09-29 | 22 | 100% | bar: Noon 8 to Noon 8
6.3 | Add technical notes and version control logs | Nguyen The Kiet | 2026-09-24 | 2026-09-29 | 16 | 100% | bar: Noon 8 to Noon 5
6.5 | Prepare a complete project report | Huynh Nhat Duy | 2026-09-24 | 2026-09-29 | 18 | 100% | bar: Noon 8 to Noon 6
7 | Demo Preparation & Submission |  |  |  |  | 15 hours
7.1 | Record demo video (.mp4) showing all features | Tran Quoc An | 2026-09-24 | 2026-09-29 | 16 | 100% | bar: Noon 5 to Morning 2
7.2 | Edit and finalize video | Nguyen The Kiet | 2026-09-24 | 2026-09-29 | 14 | 100% | bar: Night 10 to Noon 6
7.3 | Prepare the submission package (source code, Unity packages, assets) | Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 14 | 100% | bar: Night 10 to Noon 6
7.4 | Final review of all deliverables (report + project + video) | All | 2026-09-24 | 2026-09-29 | 14 | 100% | bar: Night 10 to Noon 6
7.5 | Submit project | Trinh Tan Loc | 2026-09-24 | 2026-09-29 | 8 | 100% | bar: Morning 3 to Noon 6